## Description Sheet
| Development Changes in PD-Phase 产品开发更改 | [5 empty] | Edition 2.0
Confidential
[5 empty] | DC No. / 开发更改编号: | RBCE-PDECR2026006
Affected domain / 影响的开发域 |  |  |  |  | Date /日期: | 2026.03.25
Step 1: Change request & Basic information
Customer project Name/ 客户项目名称： |  | JP360 | MCR No. / MCR号:
Affect Product No. / 产品号: |  |  | Component No. / 零部件号:
F03ZS0000B-04 |  |  | F03Z20046V-01
Sample type / 样品类型: |  |  | Initiator/发起人: | FENG Ying
Reason of changes / 更改理由:
导油环回油口处未设计倒角，入机壳时导油环发生卡滞，压装不到位
Customer request / 客户要求 |  | Supplier request / 供应商请求 |  | Design optimization / 设计优化
Correction / 更正(错误) |  | Process / 工艺 | Other / 其它
Step 2: Change proposal & Change discription
当前设计 |  |  | 更改建议 |  |  |  | 备注
回油口增加C角和圆角，避免压装发生卡滞
回油口无倒角 |  |  | 回油口增加：C角1x45°和圆角R1
B
C
A
FD
SYS
ME
HW

## Impact analysis&QAC
| Impact analysis 影响分析 | [6 empty] | Edition 2.0
Confidential
[6 empty] | Corresponding DC No. / 对应的开发更改编号: | RBCE-PDECR2026006
[6 empty] | Date /日期: | 2026.03.25
Step 3.1 Impact analysis / 影响分析
1. Function&Performance will be influenced? / 产品功能性能影响? | [5 empty] | Confirmed by: __FENG Ying________
2. Interface and Apperance will be influenced? / 接口和外观影响? | [5 empty] | Confirmed by: __FENG Ying________
3. Reliability and robustness will be influenced? / 产品可靠性、鲁棒性影响?
Description of above points, and concern point analysis / 对上述影响的描述, 以及分析是否存在顾虑点
产品可靠性提高
4. Others component will be influenced? / 影响其它零部件? | [5 empty] | Confirmed by: __FENG Ying_________
If yes, Which components will change in parallel? 如果影响， 哪些零部件也需要同时变更?
5. Manufactory/assembly/testing will be influenced? / 加工, 装配, 测试是否影响? | [5 empty] | Confirmed by:__HU Bin_______
6. Influence on supplier part？ Feedback from Supplier/Purchasing？ | [5 empty] | Confirmed by:__ZHANG Lijuan______
采购件变更
7. Influence on System/Hardware/Software/Calibration/Mechnical parts？ | [5 empty] | Confirmed by:_FENG Ying__________
e.g.: If changes influnce software/calibration, and ME/HW version alignment is required. e.g. SW reflashing affected products in stock e.g. Mechanical change or HW change triggered SW change, inform SW team e.g. System element change trigger calibration change, inform Calibration team
8. Influence on cost / 对成本的影响
成本不变
9. Stock/Delivery treatment / 库存(发货)处理指示:
Mixed Deliveries Permissible? 改前改后是否可以混合供货？ YES NO
How to deal with 1st delviery after change? 改后第一批货物的发货要求？ Answer回答：____维持一样__________
Raw materials: | Not affect Use in other products Scrap Rework Use up
Parts/Subassemblies: | Not affect Use in other products Scrap Rework Use up
Finished goods(inhouse): Not affect Scrap Rework Use up
Finished goods(RDC外库): Not affect Scrap Rework Use up
Finished goods(customer): Not affect Recall Rework
Step 3.2 Quality Assurance Items / 检查项目
Validations 验证 |  | Plan finish date 计划完成日期 |  | Resp.person 负责人 |  | Comments 备注
Trial Run |  | 2026.04.02 |  | Hu Bin |  | 报告体现压装深度数据
Capability Studies_ CMK
Capability Studies_ MSA
MAE release
Cleanness test
QZ test
200h PDL
BOM check
Test report
PAV release
Step 3.3 Affected documents Check/ 影响文档检查
1 Interface FMEA-relevant / IFMEA: |  |  |  | Resp.person: |  |  | Due date: _______
2.Product FMEA-relevant / DFMEA: |  |  |  | Resp.person: |  |  | Due date: _______
3. Special Charecteristics relevant/PSC: |  |  |  | Resp.person: |  |  | Due date: _______
4. IMDS relevant: |  |  |  | Resp.person: |  |  | Due date: _______
5 Offer drawing relevant: |  |  |  | Resp.person: |  |  | Due date: _______
6. TCD relevant: |  |  |  | Resp.person: |  |  | Due date: _______
7. Norm, WB, HF... relevant: |  |  |  | Resp.person: |  |  | Due date: _______
8 … |  |  |  | Resp.person: |  |  | Due date: _______
Step 4 Technical feasibility & Validation plan approval / 技术可行性&验证计划批准
Development/ 研发 | Purchasing/采购 |  | MFE/工艺 | Quality/质量 | CPjM/客户项目 |  | COS/样品
XIANG Liangshan | TAO Jiong |  | HE Yonggang | XIA Qian | SU Jian |  | HE Yonggang
MOEx/ 生产 | LOG/物流 |  | Others (in needed)
LUO Zhi | XU Baochun
* Note: if reflash SW in joint location, e.g. in ME plant, the max. 2 resp. are needed to approve the PD-ECR, e.g. MOE DM +EPQ
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
no/否
yes/是
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
increase/增加
decrease/降低
no change/不变
yes/是
no/否
(包含在途)
(包含在途)
yes/是
no/否
no/否
yes/是

## Implementation
|  | Implementation 导入确认 | [6 empty] | Edition 2.0
Confidential
[7 empty] | Corresponding DC No. / 对应的开发更改编号: | RBCE-PDECR2026006
[7 empty] | Date /日期: | 2026.03.25
Step 5 Documents release / 文档发布
1. Documents release (drawing, offer drawing, Bom, Spec., ) / 文档发布 (图纸, 客户图纸， …)
Development confirmation/ 研发确认: ___FENG Ying_______
Step 6.1 Implementation check list / 导入清单
Departments | Y/N | Description | [5 empty] | Responsible | Due date
Development | N | Change BOMs & Drawings & Documents in POE system | [5 empty] | FENG Ying
| N | Inform documents update (check work-on can met requirements) | [5 empty] | FENG Ying
| Y | Update Offer drawing, TCD, D-FMEA
| N | Norm, WB, HF...
| N | MoC，IMDS.
Manufacturing | Y | Related (Production/Testing) equipement be ready on site
| Y | Related (Production/Testing) program be ready ( If related to lettering, labeling or marking change, it's mandatory to provide the change evidence in Remark column)
| Y | Related (Production/Testing) tooling / cutting / fixture etc. be ready
| Y | Old tooling / cutting / fixture disposal
| Y | Old materials disposal
| Y | Planner update the planning sheet
| Y | Update FMEA
| Y | Update CP/FC (Control Plan/Flow Chart)
| Y | Update WI/PDS (Include attachments.)
| Y | First batch Mark, Special Mark (Inside Package)
| Y | First batch Mark, Special Mark (Outside Package)
| Y | Training
COS | Y | Confirm the storage of old parts and coordinate the introduction date for new part (RM)
| Y | Confirm the delivery date of old parts and first delivery of new parts (FG)
| Y | Check sample orders which affected:material order of CKD
| Y | Confirm production scheduling according to the alignment, any changes share the information to MOEx,MFE
| Y | Confirm the old stock/ do prioritize delivery and inventory handling
| Y | Inform the first delivery to PMO
Purchasing | Y | Check sample orders which affected: material order of purchasing parts
| Y | Inform internal related departments(COS,MFE,MOEx)with following requirements.:Yellow sticker, delivery quantities and date, PN No. and name,change description…
| Y | Update incoming inspection plan
Quality | Y | Update testing programe on testing equipment
| Y | Update inspection plan for CKD parts
CPjM | Y | Distribute the Offer drawing, TCD to customer
LOP | Y | Check 10 digit material order
PMO | Y | Check sample orders which affected: Customer order
| Y | Inform Customer the first delivery information
Others (e.g. actions in HW, SW)
Step 6.2 Implementation date / 执行日期
Planned implementation date: 变更计划执行日期_____________
Step 7 Implementation approval / 导入清单
Development/ 研发 |  | Purchasing/采购 | MFE/工艺 | COS/样品 | Quality/质量 | CPjM/客户项目 |  | MOEx/生产 | LOG/物流
XIANG Liangshan |  | TAO Jiong | HE Yonggang | HE Yonggang | XIA Qian | SU Jian |  | LUO Zhi | XU Baochun
Other/其他
\

## Example of affected actions
Example of affected actions
Related domains | PD-ECR check points | Team discusstion results to be documented
ME | Step 3.1 Impact analysis / 影响分析 5. Manufactory/assembly/testing will be influenced? / 加工, 装配, 测试是否影响?
Specific analysis points | a. whether production fixture needs to consider Poka Yoke to prevent manual assembly with wrong direction in Types change? b. whether change over check list needs to prepare for operators when type changes? c. whether the PLC program and working parameter for Screw tightening needs updating? d. whether additional assembly/testing risks by the change?
HW | Step 3.2 Quality Assurance Items / 检查项目
Specific analysis points | a. BOM check b.Test report c. PAV release
SW | Step 3.1 Impact analysis / 影响分析 5. Manufactory/assembly/testing will be influenced? / 加工, 装配, 测试是否影响?
Specific analysis points | SW reflash operation needs to do: - Scenario 1 (Highest efficient way): Rework at Customer side, reflash SW at EOL station or by OTA. - Scenario 2: Return to Bosch Plant: Rework at internal area for SW reflash, key points to be defined: Rework site, Operator, ReflashTool, necessary Documents, RASIC
SW | Step 6.1 Implementation check list / 导入清单
Specific analysis points | SW introduction to Production: 1. RBCD(Calibration engineer) offline deliver updated SW code by mail to ME plant for try run 2. ME upload to manufacturing SW flash station (interface?) 3. ME try run with the new upgrated SW and feedback result to RBCD 4. officially send upgrated SW to ME via workon during PD-ECR approval (2days) (update SW if need based on the try run result)
SW | Step 6.1 Implementation check list / 导入清单
Specific analysis points | e.g. Machanic electrical valvel design changed, triggered SW version updated, Prevention defined to prevent from Label/type error: add SW identification code into Barcode for ensuring traceability

## History of Template
Nr. | Change content | version | Date | Editor
1 | Initial version | v1 | Apr. 2025 | Shi Kai (RBCD/EFC2)
2 | 1) Change scope cover SYS,ME, HW 2) Add linkage of SW activity | v2 | Dec. 2025 | Shi Kai (RBCD/EFC2) Fan Xiaofeng (RBCD/ETC6)