## Description Sheet
| Development Changes in PD-Phase 产品开发更改 | [5 empty] | Edition 06
Doc. Approval: RBCD/EIS
Confidential |  |  |  |  | Effective date: 20250714
[5 empty] | DC No. / 开发更改编号: | PDECR_0060
[5 empty] | Date /日期: | 20251125
Step 1: Change request & Basic information
Customer project Name/ 客户项目名称： |  | Geely，CNHTC，XCMG | MCR No. / MCR号: |  | BM-00095101_005
Affect Product No. / 产品 |  |  | Component No./ 零部件号: |  | F01ZD302X-01,'F01ZD302Y-01
F01Z7P001R-01,F01Z7P001Y-01,F01Z7P001P-01,F01Z7P001T-01
Sample type / 样品类型: |  |  | Initiator/发起人: | 王小龙
Reason of changes / 更改理由:
1. 800V控制器从B1变到B2；除SiC，SiC holder，三相接线柱外，壳体，陶瓷片，密封垫，O型圈等沿用600V开模件；
Customer request / 客户要求 |  | Supplier request / 供应商请求 |  | Design optimization / 设计优化
Correction / 更正(错误) |  | Process / 工艺 | Other / 其它
Step 2: Change proposal & Change discription
1. 800V控制器从B1变到B2；除SiC，SiC holder，三相接线柱外，壳体，陶瓷片，密封垫，O型圈等沿用600V开模件；
B
C
FD
A
before
800V B1
PN:
F01ZD00018-01
after
800V B2
PN:
F01ZD00018-02
F01ZD0000E-02
F01ZD0000F-02
F01ZD0000G-02
外形与600V一致

## Description Sheet (2)
| Development Changes in PD-Phase 产品开发更改 |  |  | Edition 06
Doc. Approval: RBCD/EIS
Confidential |  | Effective date: 20250714
|  | DC No. / 开发更改编号: | PDECR_0058
|  | Date /日期: | 20251125
Step 2: Change proposal & Change discription
before
F01ZD3002V-01
after
F01ZD3002V-02
before
F01ZD3002Z-01
after
F01ZD3002Z-02
电气间隙Min. 3.4mm<4.0mm
电气间隙Min. 4.1mm>4.0mm
适配600V壳体及陶瓷片局部尺寸调整
爬电距离MIn7.4>7.3mm

## DC Review_page1
| Development Changes in PD-Phase 产品开发更改 | [7 empty] | Edition 06
Doc. Approval: RBCD/EIS
Confidential | [6 empty] | Effective date: 20250610
[7 empty] | DC No. / 开发更改编号: | PDECR_0060 | 0
[7 empty] | Date /日期: | 20251125 | 0
Step 3.1 Impact analysis / 影响分析
1. Function&Performance will be influenced? / 产品功能性能影响?
If Yes, product impaction evaluation? 如果是，产品影响评估？(如果是初次样件放行，空白处请说明样件目的） |  |  |  |  | PCBA变更见PDECR_138_eCom_800V_B2； 爬电距离要求更高； |  |  | Testing /签名_______
Whether need sample to test? Plan？ 是否需要样件进行验证？计划？ |  |  |  |  | DV测试，绝缘耐压测试；ECM测试，计划12.05完成
2.1 Interface&boundary to customer will be influenced? / 接口&边界是否影响客户?
Please explain the impact and whether it has been confirmed by the customer?请说明影响和是否得到客户的确认？ |  |  |  |  | B1-->B2外形变化，需通知客户（仅吉利有B1状态） |  |  | Customer PM /签名_______
2.2 Interface&boundary to internal will be influenced? / 接口&边界是否影响内部?
If Yes, internal impaction evaluation? 如果是，内部影响是否评估？(例如： 测试接头，噪音测试夹具等） |  |  |  |  | 待确认 |  |  | Testing/签名_______
3. Mechanical strength&Durability will be influenced? / 产品可靠性、鲁棒性影响 ？
If Yes, How to evaluate？Plan? 如果是，请说明影响和如何评估,计划？ (例如:仿真分析等) |  |  |  |  | DV测试，绝缘耐压测试；ECM测试 |  |  | Validation/签名_______
Whether need new sample or fixture to test? Plan？ 是否需要样件以及定制/改制夹具进行验证？计划？ |  |  |  |  | 样件已准备好
4. Others component will be influenced? / 影响其它零部件?
If yes, Which components will change in parallel? 如果影响， 哪些零部件也需要同时变更? 不影响
5. Manufactory/assembly/testing will be influenced? / 加工,装配,测试是否影响?
Feedback from manufacturing engineer? 生产制造装配是否影响，反馈？ | [7 empty] | Production/签名_______
1，气密规范及内腔容积提供给生产；2，生产确认气密研发提供的气密规范是否需要调整程序；3.吉利总成需体现软硬件版本变化
Influence on project&product delivery time? 对项目&产品交货时间的影响？
不影响
Influence on manufacturing cost / 对生产成本的影响?
6. Influence on supplier part？ Feedback from Supplier/Purchasing？
Was this change confirmed with Purchasing (Supplier) for feasibility? Feedback from Supplier？ 变更后的零件，生产可行性供应商是否确认？反馈？ | [7 empty] | PPS for purchase parts/签名 _______ (Below only for DCAC) DCAC Mech. 签名 _______ DCAC软/硬件 签名 _______ Quality: 签名 _______
可生产
Influence on purchasing part delivery time? 对采购件交货时间的影响？
不影响
涉及到变更的零件，博世已出PR ，供应商还未来得及生产的订单，是否已经通知供应商取消.
7：Does the change influence on purchasing cost ? 变更对采购成本的影响?
8. Changed parts Stock& treatment / 需要变更零件的库存统计和处理？ (只针对涉及到已经生产过的零件变更，新放行零件和本条不相关)
RBCW仓库和RBCD仓库，是否有库存， |  |  | 老库存消耗完，不能混合发货 |  |  |  |  | COS /签名_______
供应商处是否有库存， |  |  | ？？？ RBCD老库存消耗完，不能混合发货,ME待确认 |  |  |  |  | PPS /签名 _______
在途，运输中是否有库存
被影响到的实物库存处理指示: (设计工程师组织会议讨论) | [7 empty] | PPS for purchase parts/签名 _______ Quality for DCAC:/ 签名 _______
9. DFMA & Sample prodcution OPL?
DFMA 会议纪要，请附件说明；如果变更无需DFMA或前期PDECR已经做过DFMA，请说明并列出之前的PD_ECR号 Any OPL not closed from last time sample production? 上次样件生产是否仍有OPL没有完成？请说明或者附件说明
无
10. PM alignment？(Influence on project Timeline? Cost?); 是否同意对项目时间和成本的影响____________; 需求样品订单数量____________ ; | [7 empty] | PM/签名_______
11. 如果涉及以下情况需TCR3 审核确认。 不涉及则
Step 3.2 Quality Assurance Items / 检查项目
Validations 验证 |  | Plan finish date 计划完成日期 |  | Resp.person 负责人 |  | Comments 备注 |  | QMM/签名_______ME
Capability Studies_ CMK | [5 empty] | NA待ME确认
Capability Studies_ MSA | [5 empty] | NA
MAE release | [5 empty] | NA
Cleanness test | [5 empty] | NA
QZ test | [5 empty] | NA
200h PDL | [5 empty] | NA
Test program or fixture etc. | [5 empty] | NA
Step 3.3 Affected documents Check/ 影响文档检查
1 Interface FMEA-relevant / IFMEA: |  |  |  |  | Resp.person: |  |  | Due date: _______
2.Product FMEA-relevant / DFMEA: |  |  |  |  | Resp.person: |  |  | Due date: _______
3. Special Charecteristics relevant/PSC: |  |  |  |  | Resp.person: 王小龙 |  |  | Due date: _______ | 12.05
4. IMDS relevant: |  |  |  |  | Resp.person: |  |  | Due date: _______
5 Offer drawing relevant: |  |  |  |  | Resp.person: |  |  | Due date: _______
6. TCD relevant: |  |  |  |  | Resp.person: |  |  | Due date: _______
7. Norm, WB, HF... relevant: |  | PMB |  |  | Resp.person: Zhu Qiangmin |  |  | Due date: _______ | 12.01
Step 4 Technical feasibility & Validation plan approval / 技术可行性&验证计划批准
Design team leader |  | Development SM |  |  |  | SMP-TMS |  | TCR3
Signature / 签名: |  | Signature / 签名: |  |  |  | Signature / 签名: |  | Signature / 签名:
yes/是
no/否
yes/是
no/否
no/否
无库存
有库存, 库存数量____________
yes/是
报废
改制后使用
无库存
有库存, 库存数量____________
无库存
有库存, 库存数量____________
yes/是
no/否
涉及到已经生产过的零件变更
NA.(新零件放行,不涉及库存)
yes/是
no/否
可以继续使用完
改制费用_______
报废成本______
N.A
库存报废,金额________;
采购成本增加,金额___________;
生产成本增加,金额__________
Increase/增加 ,金额__________________
Decrease/降低 ,金额_____________________
No change/不变
yes/是
no/否
Decrease/降低 ,金额___________________
no change/不变
Increase/增加，金额___________________
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
yes/是
no/否
no/否
yes/是

## Implementation
|  | Implementation 导入确认 |  |  |  |  | Edition 06
Doc. Approval: RBCD/EIS
Confidential |  |  |  |  | Effective date:20250610
|  |  |  | DC No. / 开发更改编号: |  | PDECR_0060 | 0
|  |  |  | Date /日期: |  | 20251125 | 0
Step 5 Documents release / 文档发布
1. Documents release (drawing, offer drawing, Bom, Spec., ) / 文档发布 (图纸, 客户图纸， …)
Development confirmation/ 研发确认: __________
Date /日期:
Step 6.1 Implementation check list / 导入清单
Departments | Y/N | Description |  |  |  | Responsible | Due date
Development | Y | Change BOMs & Drawings & Documents in POE system |  |  |  | 王小龙 | done
| N | Inform documents update (check work-on can met requirements) |  |  |  | 王小龙 | done
| N | Update Offer drawing, TCD, D-FMEA |  |  |  | 范嫦娥 | 暂定12.07
| N | Norm, WB, HF... PMB |  |  |  | NA
| N | MoC，IMDS. |  |  |  | 王小龙 | 12.09
Manufacturing | N | Related (Production/Testing) equipement be ready on site |  |  |  | NA
| N | Related (Production/Testing) program be ready ( If related to lettering, labeling or marking change, it's mandatory to provide the change evidence in Remark column) |  |  |  | Wu Zhaohui | 12.12
| N | Related (Production/Testing) tooling / cutting / fixture etc. be ready |  |  |  | NA
| N | Old tooling / cutting / fixture disposal |  |  |  | NA
| N | Old materials disposal |  |  |  | NA
| N | Planner update the planning sheet |  |  |  | NA
| N | Update FMEA |  |  |  | NA
| N | Update CP/FC (Control Plan/Flow Chart) |  |  |  | NA
| N | Update WI/PDS (Include attachments.) |  |  |  | NA
| N | First batch Mark, Special Mark (Inside Package) |  |  |  | NA
| N | First batch Mark, Special Mark (Outside Package) |  |  |  | NA
| N | Training |  |  |  | NA
COS | N | Confirm the storage of old parts and coordinate the introduction date for new part (RM) |  |  |  | NA
| N | Confirm the delivery date of old parts and first delivery of new parts (FG) |  |  |  | NA
| N | Check sample orders which affected:material order of CKD |  |  |  | NA
| N | Confirm production scheduling according to the alignment, any changes share the information to MOEx,MFE |  |  |  | NA
| N | Confirm the old stock/ do prioritize delivery and inventory handling |  |  |  | NA
| N | Inform the first delivery to PMO |  |  |  | NA
PPS (PPS->PMQ/PQA) | N | Check sample orders which affected: material order of purchasing parts |  |  |  | NA
| N | Inform internal related departments(COS,MFE,MOEx)with following requirements.:Yellow sticker, delivery quantities and date, PN No. and name,change description… |  |  |  | NA
| N | Update incoming inspection plan |  |  |  | NA
QMM1 | N | Update testing programe on testing equipment |  |  |  | NA
| N | Update inspection plan for CKD parts |  |  |  | NA
EIS4 | N | Distribute the Offer drawing, TCD to customer |  |  |  | NA
LOP | N | Check 10 digit material order |  |  |  | NA
PMO | N | Check sample orders which affected: Customer order |  |  |  | NA
| N | Inform Customer the first delivery information |  |  |  | NA
Step 6.2 Implementation date / 执行日期
Planned implementation date: 变更计划执行日期_________________预计12.15___________________

## Signature process
Step | PEP milestones |  |  | Process | RASIC |  |  | Comments
[5 empty] | Customer | Sales | Purchasing
| Design FMEA | Proses FMEA
[8 empty] | Business plan based on capacity information. | Assign and allocate FMEA capacities for the section. Assign FMEA moderators for the FMEA.
1 | [7 empty] | Folder Link PDECR_Overview Folder | https://teams.microsoft.com/l/channel/19%3A4qf8squd35LVjVygRGnQzEr5Qn_wfJ6wElaGf74oXLQ1%40thread.tacv2/09_PDECR?groupId=b3a5bd45-54ce-4c12-b6f8-07fbcf717dce&tenantId=0ae51e19-07c8-4e4b-bb6d-648ee58410f4&ngc=true&allowXTenantAccess=true
2 | [7 empty] | Template
3 | [5 empty] | S |  | -
4 | [7 empty] | Folder Link | 09_PDECR ¦ e-Compressor SE team ¦ Microsoft Teams
5 | [7 empty] | Signature area
6
7
8
9 |  |  | (1) |  |  |  |  | - | -
(2)
PDECR regular meeting
1： Reivew变更
2：确认签字相关方
将Review 的文件存储到对应folder,并发送相关PDF link，启动签字流程
发起工程师和校对工程师签字
Manger level 签字
worklevel 执行负责人签字
End
Allocate der FMEA moderator capacities
Work level 签字
PDECR 内容准备
在PDECR overview 中
1：登记变更内容，取变更号
2：建立对应folder
签字可手签，也可通过存放在folder 里面发送pdf 版本文件通过e-signatrure 签.

## Signature Matrix
Matiix
| 本体开发 |  |  |  |  | 生产 |  | 采购 | Cos | 内部质量 | 客户项目经理 | 平台项目经理
| Core group 设计 | 电机设计 | 控制器设计 | 测试 | 验证 | 机加工 | 装配测试
工程师 | Ku Qiong (RBCD/EIS4) Fan change (RBCD/EIS4) Li Pingzheng (RBCD/EIS4) Wang Xiaolong (RBCD/EIS4) | LI Xin (RBCW/ENG-CV2) | ZHENG Xinjie (RBCD/PJ-EPE3) | LI Bing (RBCD/EIS3) | LI Ke (RBCD/ETC6) | ZHANG Bing (RBCD/MOE1.4) | LI Ke (RBCD/MOE3) | ZHENG Xuan (RBCW/PUR3) | Meng Fanlong (RBCD/COS) | Zou Lizhu(RBCD/QMM1.1) | Qian Jiong (RBCD/EIS2) | Xu Chen (RBCD/EIS4)
SM | Lu Yang (RBCD/EIS4 RBCW/ENG-TMS) | JIANG Xingkai (RBCW/ENG-CV2) | JIANG Xingkai (RBCW/ENG-CV2) | YUAN Senqi (RBCD/EIS3) | JIANG Ningtao (RBCD/ETC6) | GAO Tong (RBCD/MOE1.1) | X | YIN Ning (RBCW/PUR3) | Zhao Lei (RBCD/COS) | MAO Yiyi (RBCD/QMM1.1) | X | X
DM | WU Xiaojian (RBCD/EIS RBCD/EIS4) |  | X | X | X | HUA Guanqun (RBCD/MOE1) | Sun tie (RBCD/MSE1-I) | X | X | X | X | WU Xiaojian (RBCD/EIS RBCD/EIS4) XIE Youfu (RBCW/TCR3)
|  | Send list | Inform list | Implementation
| PM | - | Xu Chen (RBCD/EIS4) | Send to work level person with OPL and CC to others
| Customer TPM | Qian Jiong (RBCD/EIS2)
| Core group design | Ku Qiong (RBCD/EIS4) Fan change (RBCD/EIS4) Li Pingzheng (RBCD/EIS4) Wang Xiaolong (RBCD/EIS4)
| Motor design | LI Xin (RBCW/ENG-CV2) | JIANG Xingkai (RBCW/ENG-CV2)
| DCAC design | Fu bowen （RBCW/ENG-CV1) Zheng xinjie(RBCD/PJ-EPE3) | JIANG Xingkai (RBCW/ENG-CV2)
| Platform testing | LI Bing (RBCD/EIS3) | YUAN Senqi (RBCD/EIS3)
|  | LI Ke (RBCD/ETC6) | JIANG Ningtao (RBCD/ETC6)
| Quality | Zou Lizhu(RBCD/QMM1.1) | MAO Yiyi (RBCD/QMM1.1)
| MOE | ZHANG Bing (RBCD/MOE1.4) | GAO Tong (RBCD/MOE1.1)
| COS | Meng Fanlong (RBCD/COS) | Zhao Lei (RBCD/COS)
| Purchasing | ZHENG Xuan (RBCW/PUR3) | YIN Ning (RBCW/PUR3)
| Sales | Sales（acc.to project） | Jia Kebin（RBCW/SMP-ATS1)
| Development |  | WU Xiaojian (RBCD/EIS RBCD/EIS4)
| Assembly | /LI Ke (RBCD/MOE3) CC:/Xia Liujun (RBCD/MOE3.3) | Sun Tie (RBCD/MSE-1)
| TCR |  | XIE Youfu (RBCW/TCR3)